## Active Projects
# | Project Number | Project Name | Standards | Background | Dates/Actions | Priority | Subject Matter | FERC Deadline | Relevant Orders | ERCOT Region Representatives
1 | 2016-02 | Modifications to CIP Standards ¦ Virtualization | CIP-002-7 CIP-003-Y CIP-004-8 CIP-005-8 CIP-006-7 CIP-007-7 CIP-008-7 CIP-009-7 CIP-010-5 CIP-011-4 CIP-013-3 | The CIP standards are based primarily on concepts dating back to Version 1 and as technology has evolved, issues have begun to arise as entities attempt to take new concepts and fit them into some of the Version 1 paradigms. These issues revolve around topics such as: • Hypervisor – the virtualization component that manages the guest operating systems (OSs) on a host and controls the flow instructions between the guest OSs and the physical hardware. • Virtual machines – With virtualization technologies, a single physical Cyber Asset can be used as an execution platform for numerous virtualized operating systems, micro-service containerized applications, and virtual network functions of all classifications. A single physical Cyber Asset can appear to an external network as many complete Cyber Assets. Virtual switches and networks can be defined so these virtual machines can communicate with each other as if they are separate physical nodes on the network. Virtual machines and functions can also migrate around a physically clustered cyber system such that the singular physical Cyber Asset where an application resides can change at any moment. The virtualization of Cyber Assets provides advantages for the availability, resiliency, and reliability of applications and functions hosted in such an environment and the CIP standards must not stand in the way of these benefits as long as they are implemented in a secure manner. Virtualization affords enhanced security in some cases as the security controls themselves can be virtualized and placed within the virtual environment closer to the workloads they are protecting. However, there are also different security risks introduced by these environments. The management systems or consoles for these environments allow for the complete control of numerous components of the infrastructure. Virtual machines or networks can be added, modified, or deleted from one central management system. For example, rogue virtual components can starve legitimate workloads of the shared resources (processor, memory, etc.) they need to reliably perform their function. In summary, changes to the CIP Requirements may be needed to account for virtualization. • Virtual Networks – Electronic Security Perimeter (ESP) constructs within the current CIP standard are limited to defining security zones at Open Systems Interconnection (OSI) Layer 3 and do not support security zones defined at layers other than OSI Layer 3. With current, widely deployed technology, networks are no longer solely defined by the arrangement of physical hardware and cables inside or outside of a perimeter. Networks can exist as a mixture of physical and virtual segments or purely in a virtual state within one device. Virtual firewalls and other security tools are also available to help secure these environments. Typical hardware network switches can be configured with internal logical isolation to implement multiple virtual networks within them. Accordingly, the SDT is reviewing the CIP standards to validate that definitions, requirements, and guidance regarding ESPs and Electronic Access Points (EAPs) continue to provide for secure and reliable operations. • Virtual Storage – Historically, servers were limited to dedicated storage within the device. Typically, the operating system and the applications resided in the server on hard drives. Virtual storage technologies such as Storage Area Networks (SANs) present virtualized logical drive storage units to all attached servers. These types of environments then become a shared resource among many physical and virtual hosts. | 7/10/2024: NERC Filed Petition for Approval 4/12/2024 CIP-002-7: 94.37% CIP-003-10: 93.63% CIP-004-8: 86.30% CIP-005-8: 75.73% CIP-006-7: 94.70% CIP-007-7: 90.24% CIP-008-7: 96.05% CIP-009-7: 95.80% CIP-010-5: 76.98% CIP-011-4: 86.21% CIP-013-3: 86.47% 11/29/2023 Additional Ballots CIP-003-010: 93.80% CIP-004-8: 84.73% CIP-005-8: 72.73% CIP-007-7: 89.32% CIP-010-5: 74.46% 10/7/2022 Additional Ballots CIP-002-7: 94.63% CIP-003-Y: 84.90% CIP-004-8: 84.60% CIP-005-8: 65.26% CIP-006-7: 92.60% CIP-007-7: 67.38% CIP-008-7: 95.67% CIP-009-7: 95.38% CIP-010-5: 46.35% CIP-011-4: 84.59% CIP-013-3: 82.88% 4/11/2022 Additional Ballots CIP-002-7: 79.90% CIP-003-Y: 73.43% CIP-004-8: 77.03% CIP-005-8: 60.83% CIP-006-7: 76.13% CIP-007-7: 61.45% CIP-008-7: 78.67% CIP-009-7: 78.42% CIP-010-5: 56.81% CIP-011-4: 79.08% CIP-013-3: 78.67% 9/1/2021 Additional Ballots CIP-002-7: 36.22% CIP-003-9: 41.55% CIP-004-7: 38.09% CIP-005-8: 20.25% CIP-006-7: 42.19% CIP-007-7: 29.40% CIP-008-7: 49.48% CIP-009-7: 49.73% CIP-010-5: 33.22% CIP-011-3: 40.16% CIP-013-3: 41.43% 3/22/2021 Initial Ballots CIP-002-7: 38.87% CIP-003-9: 48.30% CIP-004-7: 51.17% CIP-005-8: 26.30% CIP-006-7: 42.81% CIP-007-7: 42.32% CIP-008-7: 52.87% CIP-009-7: 53.26% CIP-010-5: 32.43% CIP-011-3: 47.25% CIP-013-3: 51.23% 9/26/2019 CIP-005 Comment Period 6/28/2019 White Paper Informal Comment Period 12/18/2018 Informal Comment Period 11/2/2017 Informal Comment Period 4/11/2017 Informal Comment Period | High | CIP | N/A | N/A | Jake Brown – ERCOT (member), Heather Morgan – EDP Renewables (member), Don Hunt – CenterPoint (observer), William Sanders – Texas RE (observer)
2 | 2017-01 (Phase 2) | Modifications to BAL-003-1.1 | BAL-003-3 | The second phase will address the Phase II recommendations in the SAR: Make the Interconnection Frequency Response Obligation (IFRO) calculations and associated allocations: 1) more reflective of current conditions; 2) consider all characteristics affecting Frequency Response (e.g., load response, mix and type of generation); 3) include all applicable entities; and 4) be as equitable as possible; and Frequency Response Measure (FRM): 1) ensure that over-performance by one entity does not negatively impact the evaluation of performance by another; 2) measure types/periods of response in addition to secondary Frequency Response, particularly primary Frequency Response; 3) include all applicable entities; and 4) make allocations as equitable as possible. | 6/1/2023 Additional Ballot BAL-003-3: 58.21% 9/7/2022 Initial Ballot BAL-003-3: 43.84% 4/27/2021 Informal White Paper Comments | Low | O&P |  |  | James Fletcher - AEP (member)
3 | 2019-04 | Modifications to PRC-005-6 | PRC-005-7 | The SAR proposes revisions to PRC-005-6 that provide clear, unambiguous guidance on the scope of applicability to AVR protective functions. Without clear applicability, the industry is struggling with how to implement PRC-005-6 and what testing is acceptable to meet the required maintenance activities prescribed by PRC-005-6. This topic is only applicable to a Generator Owner that owns a synchronous generating unit with an installed digital AVR. The SAR also proposes revising PRC-005-6 to add a new section under Facilities to clearly delineate the applicability of Protection Systems associated with AVR protective functions, limiting the scope of the AVR protective functions to those elements that open a breaker directly or via lockout or tripping auxiliary relays. | 7/24/2023 Initial Ballot PRC-005-7: 35.33% 8/25/2021 SAR Comment Period 2/12/2021 SAR Comment Period 7/8/2020 SAR Comment Period 8/28/2019 SAR Comment Period | Low | O&P |  |  | Cesar Huerta - AEP (member)
4 | 2020-02 | Modifications to PRC-024 (Generator Ride-through) | PRC-024-4 PRC-029-1 | The potential risk of increasing amounts of reactive power being supplied by nonsynchronous sources was identified in NERC's 2017 Long-term Reliability Assessment. In response to the concern, the Planning Committee (PC) assigned the System Analysis and Modeling Subcommittee (SAMS) to study the issue. The SAMS developed the Applicability of Transmission-Connected Reactive Devices white paper, which was approved by the PC at its December 2019 meeting. The PC Executive Committee reviewed the draft SAR from SAMS at its January meeting and subsequently approved the SAR by email vote ending on February 11, 2020. The SAR was later accepted by the Standards Committee at its March 2020 meeting. | 11/4/2024 NERC Petition 10/8/2024 NERC Board Adoption 10/4/2024 Additional Ballot PRC-029-1: 77.88% 9/30/2024 Final Ballot PRC-024-4: 86.41% 8/12/2024 Additional Ballot PRC-029-1: 52.89% 7/8/2024 Additional Ballots PRC-024-4: 82.70% PRC-029-1: 35.45% 4/22/2024 Initial Ballots PRC-024-4: 61.73% PRC-029-1: 25.37% 7/14/2022 SAR Comment Period 5/13/2020 SAR Comment Period | High | IBR | 2024-11-04 | Order No. 901 (10/19/2023)
5 | 2020-06 | Verification of Models and Data for Generators | MOD-026-2 | The NERC Inverter-based Resource (IBR) Performance Task Force (IRPTF) undertook an effort to perform a comprehensive review of all NERC Reliability Standards to determine if there were any potential gaps or improvements. The IRPTF identified several issues as part of this effort and documented its findings and recommendations in the “IRPTF Review of NERC Reliability Standards White Paper,” which was approved in March 2020 by the Operating Committee and the Planning Committee (now part of the Reliability and Security Technical Committee (RSTC)). Among the findings noted in the white paper, the IRPTF identified issues with MOD-026-1 and MOD-027-1 that should be addressed. The RSTC endorsed the SAR on June 10, 2020. Consistent with the IRPTF recommendations, the scope of the proposed SAR includes revisions to NERC Reliability Standards MOD-026-1 and MOD-027-1. Standards MOD-026-1 and MOD-027- 1 require, among other things, Generator Owners to provide verified dynamic models to their Transmission Planner for the purposes of power system planning studies. Both standards contain language that is specific to synchronous generators that is not applicable to IBRs. The IRPTF recommended revisions to clarify the applicable requirements for synchronous generators and IBRs. As such, the SAR proposes revisions to MOD-026-1 and MOD-027-1 to clarify requirements related to IBRs and to require sufficient model verification to ensure accurate generator representation in dynamic simulations. The Standards Committee accepted the IRPTF SAR and authorized posting at its September 24, 2020 meeting. Project 2020-02 Transmission-connected Dynamic Reactive Resources SAR was posted from March 30 to May 13, 2020, and members of a SAR DT were solicited. However, Project 2020-02 was paused indefinitely, and a SAR DT was not appointed. Subsequently, a second SAR involving similar standards, namely MOD-026 and MOD-027, was being drafted by the IRPTF and approved for posting in September 2020 by the Standards Committee. The Project 2020-06 Verifications of Models and Data for Generators SAR will be posted for industry comment, and additional nominees with MOD-026/027 background will be sought. A single SAR DT will be charged with determining whether to combine the two projects and drafting a combined SAR. | 11/4/2024 (IBR Definition) NERC Petition 10/8/2024 (IBR Definition) NERC Board Adoption 9/12/2024 Final Ballot Inveter-based Resource (IBR): 95.82% 8/12/2024 Additional Ballot Inverter-Based Resource (IBR): 91.57% 4/8/2024 Additional Ballots Inverter-Based Resource (IBR): 67.55% Invterter-Based Resource Unit (IBR Unit): 61.07% 1/9/2024 - Initial Ballot Definition - Inverter-based Resource: 42.82% Definition - IBR Unit: 45.04% 10/24/2023 Comment Period -IBR Definition 7/21/2023 Additional Ballot MOD-026-2: 43.85% 1/18/2023 Additional Ballot MOD-026-2: 26.05% 7/6/2022 Initial Ballot MOD-026-2: 27.85% 1/14/2021 SAR Comment Period | Medium High (IBR Definition) | IBR |  |  | Jonathan Rose - ERCOT (member)
6 | 2021-01 | Modifications to MOD-025 and PRC-019 | MOD-025-3 PRC-019-3 | The PPMVTF developed this SAR to revise MOD-025-2 to address issues regarding verification and data reporting of generator active and reactive power capability. As stated in the SAR, implementation of the standard has rarely produced data that is suitable for planning models (i.e., the stated purpose of the standard). The current MOD-025-2 verification testing activities require significant time, expertise, and coordination; however, they do not result in data that should be used by planners for modeling purposes. The SAR aims to retain testing activities are useful and focus on more effective means of collecting useful data for planning models. The Reliability, Security, and Technology Committee (RSTC) endorsed the SAR on October 19, 2020. PRC-019-2 addresses the reliability issue of miscoordination between generator capability, control systems, and protection functions. However, PRC-019-2 was developed with a bias toward synchronous generation and does not sufficiently outline the requirements for all generation resource types. The proposed Standard Authorization Request (SAR) aims to address a number of issues identified by the SPCS and revise the standard to be inclusive of all types of generation resources. The SAR was endorsed by the NERC Planning Committee (PC) on March 4, 2020. The MOD-025-2 and PRC-019-2 SARs were accepted and authorized for informal posting at the January 20, 2021 SC meeting. The appointed SAR DT will also determine how to addresses the applicable scope of Project 2020-02 Transmission-connected Dynamic Reactive Resources, which also seeks to modify MOD-025-2 and PRC-019-2. See Project 2020-02 Transmission-connected Dynamic Reactive Resources for additional background. | 6/8/2023 Additional Ballots MOD-025-3: 36.05% PRC-019-3: 46.73% 11/14/2022 Initial Ballots MOD-025-3: 26.65% PRC-019-3: 39.86% 4/2/2021 SAR Comment Period | High | IBR |  |  | Sean McCormick – Cypress Creek Renewables (member)
7 | 2021-02 | Modifications to VAR-002 | VAR-002-5 | Reliability Standard VAR-002-4.1 requires, among other things, Generator Operators (GOP) to ensure generators provide reactive support and voltage control, within generating Facility capabilities, in order to protect equipment and maintain reliable operation of the Interconnection. For dispersed power producing resources, it is not clear if a GOP is required to notify the Transmission Operator (TOP) for the status change of a voltage controlling device on an individual generating unit within a Facility comprised of numerous resources. NERC Project 2014-01 Standards Applicability for Dispersed Generation Resources revised VAR-002, Requirement R4, to clarify that it is not applicable to individual generating units of dispersed power producing resources. At the time, the IRPTF did not identify any reason why Requirement R3 (i.e., “status change”) should be treated differently than Requirement R4. The NERC IRPTF undertook an effort to perform a comprehensive review of all NERC Reliability Standards to determine if there were any potential gaps or improvements. The IRPTF identified several issues as part of this effort and documented its findings and recommendations in a white paper (see supporting documents) approved by the Operating Committee. Among the findings noted in the white paper, the IRPTF identified issues with VAR-002-4.1 that should be addressed through the standards development process. The SAR was endorsed by the Reliability, Security, and Technology Committee (RSTC) on June 10, 2020 and accepted by the SC on January 20, 2021. | 11/6/2023 Additional Ballot VAR-002-5: 51.49% 6/23/2023 Additional Ballot VAR-002-5: 52.58% 1/13/2023 Initial Ballot VAR-002-5: 51.87% 4/6/2022 SAR Comment Period 5/13/2021 SAR Comment Period | Low | O&P |  |  | David Daniels – AEP (member), Kristina Marriott – Miller Bros. Solar (member)
8 | 2021-03 | CIP-002 | CIP-002-Y | The Standards Committee (SC) has tasked the Project 2021-03 standard drafting team (SDT) with three Standard Authorization Requests (SARs) and one Request for Interpretation (RFI): 1. Transmission Owner Control Centers (TOCCs) – The SC assigned a portion of the Project 2016-02 SAR that relates to TOCCs to the Project 2021-03 SDT. That SAR portion is to review CIP-002 and evaluate the categorization of TOCCs performing the functional obligations of a Transmission Operator, specifically those that meet medium impact criteria. In addition, this SDT is assisting NERC staff in meeting the directive from the NERC Board of Trustees to conduct further study of the need to readdress the applicability of the Critical Infrastructure Protection Reliability Standards to these Control Centers to support reliability. To help meet this directive and the scope of the SAR, the SDT initiated a field test. The SC approved the Project 2021-03 Field Test Plan on November 17, 2021. 2. CIP-002 and CIP-014 – This SAR provides revisions to CIP-002 and CIP-014 to clarify the responsibility of Reliability Coordinators, Planning Coordinators, and Transmission Planners in identifying Facilities that warrant consideration under these Reliability Standards. As it relates to the Transmission Planner and Planning Coordinator functions, the language “critical to the derivation of Interconnection Reliability Operating Limits (IROLs)" should be replaced/updated to appropriately identify Facilities that, if somehow compromised, could significantly impact the reliability of the Bulk Electric System (BES). Additionally, this SAR includes a review of the applicability of Facilities identified by the Reliability Coordinator as critical to the derivation of IROLs to CIP-002 and CIP-014. The SC accepted this SAR on July 21, 2021. 3. CIP-002 SAR for Requirement R1 Parts 1.1 – 1.3 – This Standard Authorization Request is to consider if such a protocol converter meets the definition of a BES Cyber Asset by having an adverse impact to one or more facilities and the reliable operation on the BES. This includes consideration to the threat of unavailability, degradation, or misuse to a connected BES Cyber System and the aggregation of serial system-to-system communications from substations to Control Center BES Cyber Systems. As such, this project supports reliability by clarifying how these protocol converters should be categorized and if they are to reside within a defined Electronic Security Perimeter. 4. CIP-002 – This SAR seeks to revise CIP-002 to include identification and categorization of certain Cyber Assets (Electronic Access Control or Monitoring Systems, Physical Access Control Systems, and Protected Cyber Assets) associated with high and medium impact BES Cyber Systems. The SC accepted this SAR on November 17, 2021. The Project 2021-03 SDT originally included nine members, but now the team is down to five SDT members. The three supplemental SDT members would assist project 2021-03 in completing the remaining three SARs assigned to this project. | 11/22/2024 Final Ballot CIP-002-8 10/15/2024 Additional Ballot CIP-002-8: 83.05% 5/16/2024 Additional Ballot CIP-002-Y: 47.72% 11/9/2023 Initial Ballot CIP-002-Y: 32.54% 8/18/2023 SAR Comment Period 7/12/2023 Informal Comment Period 3/31/2023 CIP-002- Communications Protocol Converters SAR Comment Period 12/21/2022 Modifications to CIP-002 SAR and CIP-014 SAR Comment Period | High | CIP |  |  | Megan Sauter - Oncor (member)
9 | 2021-04 | Modifications to PRC-002 | PRC-002-5 PRC-028-1 | This project will be completed in two phases. The first phase addressed the scope regarding notifications relative to the sequence of events recording (SER) and fault recording (FR) data, and to clearly identify the BES Element owners that need to have SER and FR data for transformers and transmission lines with the associated identified bus in the Glencoe Light and Power SAR. The second phase will address gaps the Inverter-Based Resource Performance Task Force (IRPTF) identified within the PRC-002. The goal is to modify the requirements to ensure adequate data is available and periodically assessed to facilitate the analysis of BES disturbances, including in areas of the Bulk Power System (BPS) that may not be covered by the existing requirements. | 11/4/2024 NERC Petition 10/8/2024 NERC Board Adoption 9/18/2024 Final Ballots PRC-002-5: 84.2% PRC-028-1: 83.85% 8/12/2024 Additional Ballot PRC-028-1: 80.70% 6/14/2024 Additional Ballots PRC-002-5: 77.13% PRC-028-1: 46.77% 4/11/2024 Additional Ballots PRC-002-5: 79.46% PRC-028-1: 50.03% 9/14/2023 Initial Ballot PRC-002-5: 61.44% PRC-028-1: 43.33% | High | IBR | 2024-11-04 | Order No. 901 (10/19/2023)
10 | 2021-08 | Modifications to FAC-008 | FAC-008-6 | As currently written, the FAC-008 Reliability Standard and associated defined terms “Facility" and “Element" have been interpreted by some to mean that only electrical components may be considered when developing Generator Facility Ratings under R1. This could lead to planning and operational entities being provided Generator Facility Ratings that are higher than the actual output the plant is capable of, which could be detrimental to reliability during actual system emergencies. Explicitly allowing the inclusion of mechanical elements in the development of Facility Ratings will ensure Generators are rated to their most limiting element. Further, the FAC-008-3 non-formal use of the term “jointly owned" is ambiguous when compared with the industry legacy use of “jointly owned" as a purely financial and contractual obligation. This lack of clarity of intent of the standard could cause risk of facility rating gaps, misunderstanding of rating overlap requirements or gaps in facility rating coordination that could be resolved by clearly defining the technical expectations of the term “jointly owned". | 10/19/2023 Initial Ballot FAC-008-6: 28.8% 1/27/2022 SAR Comments | Low | O&P
11 | 2022-02 | Modifications to TPL-001-5.1 and MOD-032-1 | MOD-032-2 | Background Many areas of the North American bulk power system (BPS) continue to experience an increase in BPS-connected inverter-based resources (e.g., wind, solar photovoltaic (PV), battery energy storage systems (BESS), and hybrid power plants). NERC Reliability Standard TPL-001-5.1 is a foundational standard used for “establishing transmission system performance requirements within the planning horizon to develop a bulk electric system (BES) that will operate reliably over a broad spectrum of system conditions and following a wide range of probable contingencies." Transmission Planners (TPs) and Planning Coordinators (PCs) develop and use models of the electrical grid to perform planning assessments (e.g., steady-state, dynamic, and short-circuit) to develop corrective action plans for future reliability issues identified. Ensuring that the TPL-001 standard is reflective of the evolving nature of the BPS and its resource mix is paramount to ensuring reliable operation and resilience of the BPS moving forward. The NERC Inverter-Based Resource Performance Task Force (IRPTF)[1] undertook a complete review of the NERC Reliability Standards in the context of increasing levels of BPS-connected inverter-based resources and published a white paper on the outcomes and recommendations of this review in March 2020.[2] Based on the outcome of the review, it was determined that the TPL-001-4/5[3] needed clarifications “to address terminology throughout the standard that is unclear with regards to inverter-based resources" the next time the standard is revised. Considering current trends, the NERC SPIDERWG undertook a review of the TPL-001 standard considering the potential impact of distributed energy resources (DERs). This review is captured in the following RSTC-approved white paper and serves as the technical justification for the revisions suggested in this SAR: • SPIDERWG: Assessment of DER impacts on NERC Reliability Standard TPL-001 (here) This SAR proposes to update TPL-001-5.1 to address some of the issues identified in the white paper. TPL-001-5.1 does not currently require Planning Coordinators and Transmission Planners to complete Planning Assessments with adequate representation of the dynamic behavior of DERs. As the penetration of DERs increases, and based on the DER data and models available, Planning Assessments should include DERs that can potentially impact Transmission System performance assessment. NERC's “Lesson Learned: Single Phase Fault Precipitates Loss of Generation and Load", evaluating a 2019 frequency event in Southern England exacerbated by the unexpected reduction of 725 MW of IBR output and the unexpected loss of 350 MW of DER, highlights the critical importance of accurate Transmission System Planning Assessments. In July 2020, a significant quantity of solar PV facilities across a large geographic area in Southern CA reduced about 1000 MW output due to a disturbance on the bulk power system. Subsequent event analysis revealed that it was the consequence of momentary cessation and slow recovery of power. Standards enhancement has been one of the recommendations after the event analysis to ensure reliable operation of the bulk power system. As the penetration of DERs continues to increase across the North American bulk power system (BPS), it is necessary to account for the potential impacts of DERs on reliability in the planning, operation, and design of the BES. The NERC System Planning Impacts of Distributed Energy Resources Working Group (SPIDERWG) has identified the need for improved modeling of aggregate DER for planning studies (including both utility-scale and retail-scale DER) conducted by Transmission Planners (TPs) and Planning Coordinators (PCs). MOD-032-1 addresses the gathering of modeling data to perform planning assessments but the standard currently has no specific reference to DER data. This SAR proposes to update MOD-032-1 to: (1) include “data requirements and reporting procedures"[4] for DER that are necessary to support the development of accurate interconnection-wide models, (2) replace Load-Serving Entity (LSE) with Distribution Provider (DP) because of the removal of LSEs from the NERC registry criteria, and (3) enable the SDT to review any additional gaps in DER data collection with the de-registration of LSE. | 10/10/2024 Additional Ballot MOD-032-2: 41.90% 11/20/2023 Additional Ballot MOD-032-2: 39.52% 7/14/2023 Initial Ballot MOD-032-2: 41.82% 5/12/2023 TPL-001-5.1 Footnote 13.d SAR Comment Period 3/2/022 SARs Comment Period | High | IBR | 2024-11-04 | Order No. 901 (10/19/2023) | John Schmall – ERCOT (member)
12 | 2022-03 | Energy Assurance with Energy-Constrained Resources | BAL-007-1 | Energy assurance is an increasingly important aspect of a reliable Bulk Electric System (BES), but has been inconsistently defined and measured without explicit standards. The project scope will address several energy assurance concerns related to the operations, operations planning, and mid- to long-term planning time horizons which was first identified in the NERC white paper entitled Ensuring Energy Adequacy with Energy-Constrained Resources1. Today, the transition from coal and nuclear generation to wind, solar, natural gas (with and without oil back up), distributed energy resources, and hybrid (renewables plus energy storage) resources is creating a more complex scenario and highlighting the need for energy assurance. Installed generating capacity analysis alone is not sufficient to ensure a reliable supply of energy for the BES. The proliferation of intermittent renewable generation in the resource mix increases the importance of having precisely controllable resources with sufficient fuel available, ready to respond when needed. The increasing prevalence of distribution-level resources and flexible load programs introduces added volatility into energy forecasts, further complicating operations energy reliability assessments. This project will address two SARs. • Operations/operational planning time horizon (Operations SAR) • Planning time horizon (Planning SAR) | 11/4/2024 Additional Ballot BAL-007-1: 83.72% Initial Ballot TOP-003-7: 76.3% 6/24/2024 Additional Ballot BAL-007-1: 17.19% Initial Ballot BAL-008-1: 16.84% 3/11/2024 Initial Ballot BAL-007-1: 6.08% 9/28/2023 Informal Comment Period 7/21/2022 SARs Comment Period | High | IBR | 2024-11-04 | Order No. 901 (10/19/2023) | Julie Jin - ERCOT (member)
13 | 2022-04 | EMT Modeling |  | The bulk power system (BPS) in North America is undergoing a rapid transformation towards high penetrations of inverter‐based resources. Transmission Planners (TP) and Planning Coordinators (PC) are concerned about the lack of accurate modeling data and the need to perform electromagnetic transient (EMT) studies during the interconnection process and long‐term planning horizon. The growth of inverter technology has pushed conventional planning tools to their limits in many ways, and TPs and PCs are now faced with the need to conduct more detailed studies using EMT models for issues related to inverter-based resource integration issues. This SAR proposes including EMT models and studies in planning-related NERC Standards to ensure reliable operation of the BPS moving forward. | 9/13/2022 SAR Comment Period | Medium | IBR | 2024-11-04 | Order No. 901 (10/19/2023) | Ali Goharrizi - ERCOT (member)
14 | 2022-05 | Modifications to CIP-008 Reporting Threshold |  | Reliability Standard CIP-008-6 became effective on January 1, 2021, in response to FERC Order No. 8481 directing NERC to develop modifications to the Reliability Standards to require reporting of Cyber Security Incidents and attempt(s) to compromise a responsible entity's Electronic Security Perimeter (ESP) or associated Electronic Access Control or Monitoring Systems (EACMS). Since the effective date of CIP-008-6, there has not been a material change from CIP-008-5 in the number of Reportable Cyber Security Incidents or Cyber Security Incidents that were determined to be an attempt to compromise an applicable system. This project will address gaps in CIP-008-6 permitting a subjective determination of attempt(s) to compromise. The Standard Drafting Team (SDT) will modify the Reliability Standards and associated definitions as necessary to provide a minimum expectation for thresholds to support the definition of attempt to compromise. | 12/5/2022 SAR Comment Period | Low | CIP
15 | 2023-01 | EOP-004 IBR Event Reporting | EOP-004-5 | The SAR proposes enhancements to EOP-004-4 (EOP-004) focused on ensuring timely reporting by industry to the Electric Reliability Organization (ERO) Enterprise through reporting of events involving inverter-based resources (IBRs). Currently, the standard has relatively large generator loss size thresholds and uses language more suitable for synchronous generation. The SAR proposes to enhance the standard by adding clarity and lowering the generator loss threshold to encompass the lessons from widespread IBR loss events that have occurred. The NERC Inverter-based Resource Performance Subcommittee (IRPS) presented the SAR to the Reliability and Security Technical Committee (RSTC) for comment in September 2022. After responding to the RSTC comments, the IRPS resubmitted the SAR, and the RSTC endorsed the SAR on December 6, 2022. The Standards Committee accepted the SAR on January 25, 2023. | 3/27/2024 Comment Period 9/11/2023 Initial Ballot EOP-004-5: 32.34% 3/8/2023 SAR Comment Period | Medium | IBR |  |  | Patrick Gravois - ERCOT (member)
16 | 2023-02 | Performance of IBRs | PRC-030-1 | Multiple NERC disturbance reports,1 including the Odessa disturbance report,2 have identified the undesired performance of bulk power system (BPS)-connected inverter-based resources (IBRs) during grid faults, and have elaborated on the systemic and significant BPS reliability risks that this undesired performance can pose. IBRs may trip for many different reasons, may cease current injection due to inverter controls, or may have unwanted plant-level controller interactions. These types of issues have been extensively documented in the NERC reports. The resulting unexpected and unwarranted loss of generation poses a significant risk to BPS reliability. | 11/4/2024 NERC Petition 10/8/2024 NERC Board Adoption 9/27/2024 Final Ballot PRC-030-1: 70.88% 9/13/2024 Additional Ballot PRC-030-1: 69.73% 8/12/2024 Additional Ballot PRC-030-1: 76.11% 7/10/2024 PRC-030-1: 31.44% 4/18/2024 Initial Ballot PRC-030-1: 21.19% 3/23/2023 SAR Comment Period | High | IBR | 2024-11-04 | Order No. 901 (10/19/2023) | Patrick Gravois - ERCOT (member)
17 | 2023-04 | Modifications to CIP-003 | CIP-003-A | In light of cybersecurity events and the evolving threat landscape, the NERC Board took action at its February 4, 2021 meeting to direct NERC staff, working with stakeholders, to expeditiously complete its broader review and analysis on facilities that house low impact Bulk Electric System (BES) Cyber Assets. Specifically, the degrees of risk presented by various facilities that house the low impact BES Cyber Assets and report on whether the low impact criteria should be modified. To assist in this evaluation, NERC staff assembled a team of cybersecurity experts and compliance experts representative of a cross section of industry, called the Low Impact Criteria Review Team (LICRT). The LICRT's primary purpose was to discuss the potential threat and risk posed by a coordinated cyber attack on low impact BES Cyber Systems. In its report, the LICRT documented the results of the review and analysis of degrees of risk presented by various facilities that meet the criteria that define low impact cyber facilities and recommends actions to address those risks. The Board accepted the LICRT's report at its November 2022 meeting and asked that the recommendations in the report be initiated. The Standards Committee accepted the SAR at its March 22, 2023 meeting. | 11/13/2024 Final Documents Posted (no final ballot) 10/10/2024 Additional Ballot CIP-003-11: 93.89% 7/11/2024 Additional Ballot CIP-003-A: 80.58% 3/14/2024 Additional Ballot CIP-003-A: 60.34% 12/7/2023 Initial Ballot CIP-003-A: 35.04% 5/15/2023 SAR Comment Period | High | CIP |  |  | Jeffrey Sweet – AEP (member)
18 | 2023-05 | Modifications to FAC-001 and FAC-002 |  | The NERC System Performance Impacts of Distributed Energy Resources Work Group (SPIDERWG) evaluated the current body of NERC Reliability Standards and the requirements within those standards for distributed energy resource (DER) applicability and effectiveness with increasing penetrations of DER. This review is housed in the SPIDERWG White Paper: NERC Reliability Standards Review. The review took place between the years 2018 and 2022, culminating in a handful of SARs which included the SARs for FAC-001-4 and FAC-002-4. Both of these standards were identified as needing refinement, such that the reliability at the transmission to distribution interface (T-D interface) is maintained. | 9/7/2023 SARs Comment Period | Low | O&P
19 | 2023-06 | CIP-014 Risk Assessment Refinement |  | Due to an increase in reports of physical attacks on electric substations, the Federal Energy Regulatory Commission (FERC) issued the December 2022 Order in Docket No. RD23-2-000 directing NERC to evaluate the effectiveness of the Physical Security Reliability Standard CIP-014-3 in mitigating the risks to the Bulk-Power System (BPS) associated with physical attacks. In the report filed in response to a FERC directive, NERC staff identified continuing inconsistency in registered entity CIP-014-3 risk assessments to most appropriately identify critical infrastructure. FERC directed NERC to evaluate whether the physical security protection requirements in NERC's Reliability Standards are adequate to address the risks associated with physical attacks on BPS Facilities, including the adequacy of the required risk assessment in CIP-014-3 Requirement R1. In the report, NERC found that CIP-014-3 required revision to assure adequate and consistent approach in evaluating instability as well as the identification of infrastructure critical to the operation of the BPS. | 11/6/2024 Additional Ballot CIP-014-4: 47.34% 7/3/2024 CIP-014-4: 11.67% 6/8/24/2023 SAR Comment Period | High | CIP/O&P |  | Order Directing Report on CIP-014 (12/15/2022) | Brad Collard - PEC (observer) | R1-R3 - relevant to NSRF R4-R6 - relevant to CIPWG
20 | 2023-07 | Modifications to TPL-005.1 Transmission System Planning Performance Requirements for Extreme Weather | TPL-008-1 | On June 15, 2023, FERC issued a Final Rulemaking to direct NERC to develop a new or modified Reliability Standard to address a lack of a long-term planning requirement(s) for extreme heat and cold weather events. Specifically, FERC directed NERC to develop modifications to Reliability Standard TPL-001-5.1 or a new Reliability Standard, to require the following: (1) development of benchmark planning cases based on major prior extreme heat and cold weather events and/or meteorological projections; (2) planning for extreme heat and cold weather events using steady state and transient stability analyses expanded to cover a range of extreme weather scenarios including the expected resource mix's availability during extreme heat and cold weather conditions, and including the wide-area impacts of extreme heat and cold weather; and (3) development of corrective action plans that mitigate any instances where performance requirements for extreme heat and cold weather events are not met. | 11/21/2024 Additional Ballot TPL-008-1: 10/21/2024 Additional Ballot TPL-008-1: 51.9% 8/22/2024 Additional Ballot TPL-008-1: 18.17% 5/3/2024 Initial Ballot TPL-008-1: 18.69% 9/27/2023 SAR Comment Period | High | Extreme Weather | 2024-11-04 | Order No. 896 (Issued 6/15/2023) Order No. 901 | Sun Wook Kang - ERCOT (member)
21 | 2023-08 | Modifications of MOD-031 Demand and Energy Data |  | The NERC Reliability Standard MOD-031-3 seeks to “provide authority for applicable entities to collect Demand energy and related data to support reliability studies and assessments and to enumerate the responsibilities and obligations of requestors and respondents of that data." The SPIDERWG has recently recommended in the White Paper: SPIDERWG NERC Reliability Standards Review that MOD-031-3 should be revised to allow for the Planning Coordinator (PC) to obtain existing and forecasted distributed energy resource (DER) information from Distribution Provider (DP) and Transmission Planner (TP) entities. The White Paper further asserts that the TP should have the ability to act as an intermediary to provide data from DPs to the PC. This project's goal is to ensure that various forms of historical and forecast Demand, energy data, and information are available to the parties that perform reliability studies and assessments and provide the authority needed to collect the applicable data. | 11/8/2023 SAR Comment Period | Low | O&P
22 | 2023-09 | Risk Management for Third-party Cloud Services |  | From a security perspective, the electric industry landscape is facing an increase in the number and sophistication of cyberattacks and security teams are seeking tools and capabilities to improve their security programs. Security solutions with greater visibility, detection, correlation, analytics, and responsiveness are available using cloud services to help security teams to reduce potential impacts of security events and speed recovery, while also protecting data confidentiality and integrity. Cloud services can provide increased availability, including resiliency, due to the scalability, redundancy, high availability, and fault tolerance. Cloud services play a critical role in providing greater capability across the security domains. Additionally, as noted in the 2020 FERC Notice of Inquiry, the vast majority of new products from vendors are cloud-based solutions placing increased pressure on NERC registered entities to securely operate the BES. Concurrently, from an operational and reliability perspective, the modern power grid landscape is changing, driven by rapid grid modernization, digital transformation, decentralization of electric resources, and decarbonization targets. These factors are increasing the data volumes required to continue operating a reliable and resilient grid and thus increasing the need for data analytics and resources such as computing, network, and storage. Entity operations for assets across the NERC CIP impact levels will be facing the growing demands for compute capacity to manage the increasing volumes of data to respond to grid variability and maintain reliable grid operations. Increasing data storage requirements and processing requirements of grid modernization are driving the need for cloud services. Cloud resources provide Entities with expanded simulation capabilities and development environments that can help meet patching cycles and testing requirements for on premises assets under the CIP requirements. Cloud services offer fault-tolerant system design capabilities in which operations and data can be replicated and run in independent application stacks in geographically dispersed locations along with other benefits, including reliability, resilience, and security. | 7/1/2024 SAR Comment Period | Medium | CIP |  | 2020 FERC NOI
23 | 2024-01 | Rules of Procedure Definitions Alignment (Generator Owner and Generator Operator) |  | The project will address concerns regarding the reliability impacts of inverter-based resources (IBRs) on the Bulk-Power System that do not meet the current definition of Bulk Electric System (BES) and have not historically been required to be registered with NERC for compliance with the NERC Reliability Standards. Such concerns are discussed in detail in the Federal Energy Regulatory Commission (FERC) November 17, 2022 order in Docket No. RD22-4-000, in which FERC directed NERC to develop a work plan to address the registration of these IBRs and ensure their compliance with Reliability Standards by certain milestone dates. See Registration of Inverter-Based Resources, 181 FERC ¶ 61,124 (Nov. 17, 2022). In March 2024, NERC proposed changes to its Rules of Procedure registry criteria to include certain non-BES IBRs in the Generator Owner (GOs) and Generator Operator (GOP) categories. Revising the GO and GOP definitions in the NERC Glossary of Terms to match the registry criteria will ensure these previously unregistered IBRs will be subject to the NERC Reliability Standards and mitigate their impacts on the BPS. | 9/11/2024 SAR-IBR Comment Period 8/20/2024 SAR Comment Period | High |  |  | 11/17/2022 Order - Registration of Inverter-Based Resources
24 | 2024-03 | Revisions to EOP-012-2 | EOP-012 | NERC developed the original version of the generator cold weather preparedness Reliability Standard, Reliability Standard EOP-012-1, in 2022 under Project 2021-07 Extreme Cold Weather Grid Operations, Preparedness, and Coordination. The purpose of this project was to address standards-related recommendations from the Federal Energy Regulatory Commission (FERC)/NERC/Regional Entity staff review of operations during the February 2021 Winter Storm Uri event. NERC developed Reliability Standard EOP-012-2 in 2023-2024 to address Commission directives from the February 2023 order approving Reliability Standards EOP-012-1 and EOP-011-3. In the February 2023 Order, the Commission directed that NERC revise EOP-012-1 to clarify the applicability of the standard's requirements for generator cold weather preparedness, further define the circumstances under which a Generator Owner may declare that constraints preclude them from implementing one or more corrective actions to address freezing issues, and to shorten the implementation timeline so cold weather reliability risks would be addressed more quickly. On June 27, 2024, FERC issued an order approving Reliability Standard EOP-012-2. While finding Reliability Standard EOP-012-2 represented an improvement over the prior version and addressed many of its concerns, FERC found the standard requires further improvement to address certain concerns remaining from its February 2023 order. FERC therefore directed NERC to revise the standard in five areas and to submit a revised standard within nine (9) months of the date of the order, or by March 27, 2025. | 11/5/2024 Initial Ballot EOP-012-3: 42.29% 8/16/20024 SAR Comment Period | High | Extreme Weather |  | 6/27/2027 Order | David Kezell - ERCOT (Chair) Venona Greaff - Occidental (member)

## Order 901 Workplan
FERC Order 901 Workplan - filed by NERC on 1/17/2024
Milestone 2 Performance Requirements and Post-Event Performance Validation
Current Projects | Project Name | Subject- Detail - see Active Projects Tab | Date to be filed
2020-02 | Modifications to PRC-024 (Generator Ride-through) |  | 2024-11-04
2021-04 | Modifications to PRC-002 |  | 2024-11-04
2023-02 | Performance of IBRs |  | 2024-11-04
Milestone 3 Data Sharing
Proposed Project | Subject | Subject - Detail | Date to be filed
New SAR 1 | MOD-032 | Establish requirements for multiple model types Update Data Exchange Requirements Include standard model type and parameters for both aggregated IBR and DER. | 2025-11-04
New SAR 2 | FAC-001 | Update Transmission Owner data requirements to align with revised MOD-032 Transmission Owners establish and implement data aggregation methods for aggregated IBR and DER | 2025-11-04
Milestone 3 Model Validation
Proposed Project | Subject | Subject - Detail | Date to be filed
New SAR 3 | Planner/Operator | Establish requirements to evaluate actual performance to simulation. Leverage all model types. Trigger further analysis and model quality improvement data owners | 2025-11-04
New SAR 4 | Data Owner | Establish requirements for Generator Owners, Transmission Owners, Distribution Providers to analyze and improve model quality when triggered by Planner/Operator | 2025-11-04
Milestone 4 Planning and Operational Studies
Current Projects | Project Name | Subject- Detail - see Active Projects Tab | Date to be filed
2022-02 | Modifications to TPL-001-5.1 and MOD-032-1 |  | 2026-11-04
2022-03 | Energy Assurance with Energy-Constrained Resources |  | 2026-11-04
2022-04 | EMT Modeling |  | 2026-11-04
2023-07 | Modifications to TPL-005.1 Transmission System Planning Performance Requirements for Extreme Weather |  | 2026-11-04

## 901 SARs
SAR Title | Date Submitted | Part of Project | Dates/Actions
FERC Order No. 901 Milestone 3, Part 3 | 2024-04-29 | 2021-01 | 5/23/2024 - 6/28/2024 SAR Comment Period
Federal Energy Regulatory Commission (FERC) Order No. 901 – Milestone 3, Part 2: IBR Model Validation | 2024-04-29 | 2020-06 | 5/23/2024 - 6/28/2024 SAR Comment Period
Federal Energy Regulatory Commission (FERC) Order No. 901 – Milestone 3, Part 1: Modeling and Data Sharing Requirement | 2024-04-29 | 2022-02 | 5/17/2024 - 6/24/2024 SAR Comment Period